## Loyd Flores
To-do list
To be completed by: |  | 2023-12-10 |  | Name Loyd Flores
Deadline: |  | 2023-12-10 |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Group reading of project specifications | 2023-12-01 | 2023-12-01 | n/a | 1 day | Manage Ambiguity
100% | Discussion and task dissemenation | 2023-12-02 | 2023-12-02 | n/a | 1 day | Manage Ambiguity
100% | Work on assigned tables | 2023-12-03 | 2023-12-03 | n/a | 1 day | Manage Ambiguity
100% | Work on assigned tables and assist other members | 2023-12-04 | 2023-12-04 | n/a | 1 day | Manage Ambiguity & Stress management
100% | Compilation of work | 2023-12-05 | 2023-12-05 | n/a | 1 day | Leadership, collaboration
100% | Complete Assigned Views and tables | 2024-12-06 | 2024-11-08 |  | 1 day | Managing Ambiguitiy
100% | Check up on queries | 2023-12-08 | 2023-12-08 |  | 1 day | stress management
100% | presentation and submission | 2024-11-09 | 2024-11-09 |  | 1 day | stress management

## Mohammed Hasan
To-do list
To be completed by: |  | 2023-11-29 |  | Name Mohammed Hasan
Deadline: |  | 2023-11-29 |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2023-11-20 | 2023-11-20 | No revision |  | stress management
100% | Preparation | 2023-11-21 | 2023-11-21 | No revision |  | stress management
100% | udt, views, normalization research | 2023-11-24 | 2023-11-24 | No revision |  | stress management
100% | table 1 | 2023-11-25 | 2023-11-25 | No revision |  | stress management
100% | table 2 | 2023-11-28 | 2023-11-28 | No revision |  | stress management
100% | Presentation | 2023-11-29 | 2023-11-29 | No revision |  | stress management
0%
0%
0%

## Yasir J Shoeb
To-do list
To be completed by: |  | 2023-11-29 |  | Name Yasir Jawwad Shoeb
Deadline: |  | 2023-11-29 |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2023-11-20 | 2023-11-20 | 2023-11-20 |  | Met virtually to walk through project spec as a group
100% | Implement discussed code | 2023-11-21 | 2023-11-21 | 2023-11-21
100% | Implement discussed code | 2023-11-24 | 2023-11-24 | 2023-11-24 |  | researching tables and created procedures to write precise altered procedures
100% | Implement discussed code | 2023-11-25 | 2023-11-25 | 2023-11-25 |  | Procedures revised by group together
100% | Implement discussed code | 2023-11-28 | 2023-11-28 | 2023-11-28 |  | Procedures revised by group together
100% | Implement discussed code | 2023-11-29 | 2023-11-29 | 2023-11-29 |  | group created slides and presented code being executed to show functionality
0%
0%
0%

## Zhihan Chen
To-do list
To be completed by: |  | 2023-11-15 |  | Name Zhihan Chen
Deadline: |  | 2023-11-15 |  | Date
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2023-12-01 | 2023-12-01 | n/a | 1
100% | Preparation | 2023-12-02 | 2023-12-02 | n/a | 1
100% | Work with the task | 2023-12-03 | 2023-12-05 | n/a | 2
100% | powerpoint presentation | 2023-12-06 | 2023-12-06 | n/a | 1
0%
0%
0%
0%
0%

## Roni Mikhaylov
To-do list
To be completed by: |  | 2023-11-29 |  | Name Roni Mikhaylov
Deadline: |  | 2023-11-29 |  | 2023-11-29
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2023-11-20 | 2023-11-20 | No revision | 1899-12-31 | Planning on how to attack this project
100% | Preparation | 2023-11-21 | 2023-11-21 | No revision | 1899-12-31 | Preparing by assigning individual work
100% | Code Writing | 2023-11-24 | 2023-11-24 | No revision | 1899-12-31 | researching tables and created procedures to write precise views and normalized tables
100% | Meeting with group | 2023-11-25 | 2023-11-25 | No revision | 1899-12-31 | Met with the group every single day to work through issues
100% | Creaiting Views | 2023-11-28 | 2023-11-28 | No revision | 1899-12-31
100% | Presentation with group/ slides | 2023-11-29 | 2023-11-29 | No revision | 1899-12-31 | group created slides and presented code being executed to show functionality

## Kishan Shah
To-do list
To be completed by: |  | 2023-11-15 |  | Name: Kishan Shah
Deadline: |  | 2023-12-05 |  | Group 3
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2023-12-01 | 2023-12-01 | 2023-12-02 | 2days | Revision took place as a group, handled and assigned parts to all
100% | Preparation | 2023-12-02 | 2023-12-02 | 2023-12-02 | 1 day | researching tables and created procedures to write precise altered procedures
100% | Create Queries | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2 day | create stored procedure table
100% | Nomalize the Database | 2023-12-05 | 2023-12-06 | 2023-12-07 | 3day | Procedures revised by group together
100% | PowerPoint | 2023-12-09 | 2023-12-09 | 2023-12-09 | 1 day | group created slides and presented code being executed to show functionality
0%